## Read Me
Grant Proposal Timeline Template
Two timelines in one file: the project timeline a funder scores, in project months with a quarter view, and the writing schedule your team works backward from the deadline.
Version 1.0 ¦ October 2026 ¦ Published by GrantCue ¦ Free to copy, edit and share
Read this first
Illustrative figures, not data from a real organization. The sample project, an adult literacy and job-readiness program serving three cohorts on a $180,000 request across two 12-month budget periods, is a composite built to show the file working. The deadline on the Writing Timeline tab is an example date. Replace every row with your own project.
This workbook is a starting point to adapt, not legal or accounting advice. The notice of funding opportunity and the award terms decide the period of performance, the budget periods, the due dates and the reports that apply to you.
Type only in the cream cells. The blue cells are formulas: if you type over one, the file stops calculating that row.
What is in this workbook
Project Timeline. One row per funded activity: activity, start month, end month, responsible role, deliverable, and the evaluation data it produces. Formulas show which budget period each row falls in, flag rows that cross a budget-period boundary or end after the period of performance, and turn project months into calendar dates for your internal calendar once you type an award start date.
Quarter View. The same rows as a Gantt-style table built by formulas: a square marks each quarter an activity runs, a diamond marks the quarter its deliverable is due. Up to 20 quarters (60 months).
Writing Timeline. The 8-week schedule from the article, counted back from the deadline you type, with an internal due date and a status for every week, plus the dates registration and validation force on you.
Two-Week Sprint. The compressed schedule for an opportunity found late, dated from the same deadline.
Timeline Checks. The checks that catch a timeline that contradicts the budget, the evaluation plan or the reporting schedule. Some are calculated; the rest you confirm by hand.
Rules the project timeline has to respect
Use project months, not calendar dates. The award start moves, so write Month 1, never January 2027. The calendar-date columns are for your own calendar after the award notice arrives, not for the proposal.
A budget period and the period of performance are different spans. Under 2 CFR 200.1, a budget period is the time interval from the start date of a funded portion of an award to the end date of that funded portion, during which recipients and subrecipients are authorized to incur financial obligations; the period of performance runs between the award's start and end dates and may include one or more budget periods. Award notices state both (2 CFR 200.211(b)(5) and (b)(6)).
Costs other than administrative closeout costs must be incurred during the approved budget period (2 CFR 200.403(h)). An activity in month 14 staffed by a position funded only through month 12 is the contradiction a reviewer catches.
Build the timeline after the budget, and use the same nouns as the budget, the evaluation plan and the logic model, so a reviewer moving between pages never has to translate.
Dates the writing schedule cannot move
Grants.gov says you can't start applying until your organization is registered in SAM.gov, and to allow up to 10 business days for SAM registration to become active (Grants.gov, applicant registration, read October 6, 2026).
A Grants.gov submission produces a receipt email, then a validation confirmation or a rejection with errors. If no email arrives within two business days, Grants.gov says to check your spam folder and then contact support (Grants.gov, check application status, read October 6, 2026). A rejection that lands after the closing time means the deadline is missed.
The closing hour matters as much as the date. NIH states that applications are due by 5:00 PM local time of the applicant organization on the due date (NIH standard due dates, read October 6, 2026). Type the closing time from your own notice.
The business-day formulas (WORKDAY) skip Saturdays and Sundays only. Move a date by hand when a holiday falls inside it.
Reuse notes
Save a clean copy as the master. For each opportunity, copy it, type the deadline and the period of performance, and keep the copy with the opportunity record. A timeline living in somebody's inbox disappears the week they take leave.
Free to use, copy and share. No attribution required, though a link is always welcome.
More templates, worked examples and grant management tools: grantcue.com/blog
Source: https://www.grantcue.com/blog/grant-proposal-timeline-example-template ¦ GrantCue

## Project Timeline
Project Timeline
Illustrative figures, not data from a real organization. One row per funded activity, ordered by start month. Use project months (Month 1 is the award start). Type in the cream cells; the blue cells are formulas.
Project | Example Adult Literacy and Job-Readiness Project (composite)
Period of performance (months) | 24
Budget period length (months) | 12
Award start date (optional, internal calendar only)
Activity | Start month | End month | Responsible role | Deliverable | Evaluation data collected | Budget period | Crosses a budget period? | Within the period of performance? | Start date (internal) | End date (internal)
Hire instructor and coach | 1 | 3 | Program Director | Instructor and coach hired, cohort 1 enrolled
Execute partner agreements | 1 | 3 | Program Director | Signed partner agreements
Collect baseline data | 1 | 3 | Program Director | Baseline data for 30 participants | Baseline data, 30 participants
Data collection | 1 | 24 | Evaluator | Quarterly data file | Attendance, completion and placement data
Cohort 1 instruction and weekly coaching | 4 | 9 | Lead Instructor | Cohort 1 reaches 60 instructional hours; completion roster with 80% of cohort 1 completing | Attendance log, completion roster
Employer outreach | 4 | 6 | Lead Instructor | Employer partner list
Placement and coaching | 4 | 24 | Program Director | Placement tracker | Placement data
Cohort 2 recruitment | 7 | 9 | Program Director | Cohort 2 enrolled
Interim report, year 1 | 9 | 9 | Program Director | Interim report
Cohort 2 instruction | 10 | 15 | Lead Instructor | Cohort 2 completion roster | Attendance log, completion roster
Year 1 outcomes analysis and annual performance report | 10 | 12 | Evaluator | Annual performance report | Year 1 outcomes analysis
Budget period 1 closeout and year 1 financial report | 12 | 12 | Finance | Year 1 financial report
Curriculum revision from year 1 findings | 13 | 15 | Lead Instructor | Curriculum version 2 approved
Continuation request | 13 | 15 | Program Director | Continuation request
Cohort 3 recruitment and employer partnership expansion | 16 | 18 | Program Director | Enrollment roster at capacity, updated employer agreements
Cohort 3 instruction | 16 | 21 | Lead Instructor | Cohort 3 completion roster | Attendance log, completion roster
Sustainability planning | 16 | 24 | Program Director | Sustainability plan
Follow-up survey of cohort 1 graduates | 19 | 21 | Evaluator | Survey dataset with response rate | Survey of cohort 1 graduates
Interim report, year 2 | 21 | 21 | Program Director | Interim report
Final outcomes analysis | 22 | 24 | Evaluator | Final outcomes report accepted | Final outcomes analysis
Closeout: final performance and financial reports | 22 | 24 | Program Director | Final performance and financial reports
Formulas:
Start date (internal) = IF(OR(B7="",[Start month]=""),"",EDATE(B7,[Start month]-1))
End date (internal) = IF(OR(B7="",[End month]=""),"",EDATE(B7,[End month])-1)

## Quarter View
Quarter View
Illustrative figures, not data from a real organization. Built from the Project Timeline tab: ■ means the activity runs in that quarter, ◆ means its deliverable is due in that quarter (the quarter of its end month). Quarters after the period of performance stay blank.
Activity | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20
Project months | 1 to 3 | 4 to 6 | 7 to 9 | 10 to 12 | 13 to 15 | 16 to 18 | 19 to 21 | 22 to 24 | 25 to 27 | 28 to 30 | 31 to 33 | 34 to 36 | 37 to 39 | 40 to 42 | 43 to 45 | 46 to 48 | 49 to 51 | 52 to 54 | 55 to 57 | 58 to 60

## Writing Timeline
Writing Timeline: 8 Weeks From the Deadline Backward
Illustrative dates, not data from a real organization. Type the deadline; every internal due date moves with it. Each week's internal due date is the last business day before the next week starts; week 8 uses the target submission date.
Submission deadline (date) | 2027-03-15
Closing time on the deadline (from the notice) | Example: 5:00 PM local time of the applicant organization (NIH standard due dates)
Submit this many business days early | 3 | The article's rule: submit at least 3 business days early
Target submission date
If SAM.gov is not active, start registration no later than |  | Grants.gov: allow up to 10 business days for SAM registration to become active
No Grants.gov email by this date? Check spam, then contact support |  | Grants.gov: if no email arrives within two business days of submitting
Week | Countdown | Component | Owner | Week starts | Internal due date | Status | Days from today
1 |  | Read the notice end to end, confirm eligibility, verify SAM.gov is active, build a requirement checklist | Grants lead |  |  | Not started
2 |  | Go or no-go, assign sections, set internal due dates, request letters of support | Grants lead, ED |  |  | Not started
3 |  | Draft the statement of need, pull local data, draft activities and the project timeline | Program |  |  | Not started
4 |  | Draft goals, objectives, evaluation plan; build budget and budget narrative | Program, Finance |  |  | Not started
5 |  | Assemble the first full draft, reconcile timeline against budget period, inventory attachments | Grants lead |  |  | Not started
6 |  | Review against the scoring criteria, revise, chase missing letters | Reviewers |  |  | Not started
7 |  | Final edits, formatting, page-limit check, signatures, upload a draft package | Grants lead, AOR |  |  | Not started
8 |  | Submit at least 3 business days early, confirm validation emails | AOR |  |  | Not started
Registration and validation drive the last two weeks. Spare rows: type a week number from 1 to 8 and the dates fill in.
Formulas:
Internal due date = IF(OR([Week]="",B4=""),"",IF([Week]=8,B7,WORKDAY(B4-7*(8-[Week]),-1)))
Days from today = IF([Internal due date]="","",[Internal due date]-TODAY())

## Two-Week Sprint
Two-Week Sprint: Compressing When You Find the Opportunity Late
Illustrative dates, not data from a real organization. Day 14 is the deadline on the Writing Timeline tab; the other days count back from it in calendar days. Cut the sequence, not the care in any single piece: budget before narrative, one reviewer, and the last day kept free for submission problems.
First day | Last day | Tasks | From | To | Owner | Status
1 | 1 | Read the notice, confirm eligibility, verify SAM.gov and portal registrations, go or no-go, send letter requests |  |  |  | Not started
2 | 2 | Lock scope on one page: need, population, activities, outcomes, request amount |  |  |  | Not started
3 | 4 | Finance builds the budget first, fixing the scope the narrative describes |  |  |  | Not started
5 | 5 | Build the project timeline from the budget lines |  |  |  | Not started
6 | 8 | Draft the narrative: need, approach, capacity, evaluation |  |  |  | Not started
9 | 9 | Assemble attachments, chase outstanding letters |  |  |  | Not started
10 | 10 | One reviewer reads the package against the scoring criteria |  |  |  | Not started
11 | 11 | Revise from that review only |  |  |  | Not started
12 | 12 | Format, page-limit check, signatures, final package |  |  |  | Not started
13 | 14 | Submit, then hold the last day for validation errors |  |  |  | Not started
Some things will not compress. SAM.gov registration can take up to 10 business days to become active, so a lapsed one ends a two-week sprint on day one. Signatures run on somebody else's calendar, so the request goes out on day 1 with a placeholder.

## Timeline Checks
Timeline Checks
Run these before the timeline goes into the proposal. Rows 5 to 11 are calculated from the Project Timeline tab; rows 12 and 13 you confirm by hand.
Check | What to compare | Result | Fix when it fails
Period length | Timeline end month equals the period of performance |  | Extend or trim rows so the timeline covers the whole period of performance
Inside the period | No row ends after the period of performance or has its months reversed |  | Activities after the period are not fundable; closeout is the only exception
Budget boundaries | Year-boundary activities sit on the correct side |  | Split the row at the boundary, or confirm the budget funds it in both periods
Reporting | Interim and final report dates are timeline rows |  | Put interim and final report dates on the timeline as work
Verifiable milestones | Every activity has a deliverable with a number or an artifact |  | Attach a number or an artifact to every milestone
Spread across the period | Deliverables are due in the second half, not only the first |  | Spread deliverables across all quarters
Evaluation timing | Data collection points appear in the evaluation plan |  | Add a data collection row per measure, with the same wording as the evaluation plan
Staffing | Each activity's owner is funded during those months | Not checked yet | Build the timeline after the budget; move or re-fund rows whose owner is not funded
Same nouns | Row labels match the budget categories and the logic model activities | Not checked yet | Rename rows so a reviewer never has to translate between pages