## Deadline Log
Deadline Log
Rows whose internal deadline falls after the funder deadline (should be 0)
Open rows with no owner (should be 0)
Type in white cells only; gray cells hold formulas. A row stays open until its Status is Submitted, Confirmed or Missed, and a blank Status counts as open.
Deliverable ID | Award or opportunity | Funder | Deliverable type | Funder deadline | Deadline time and zone | Internal deadline | Buffer (days) | Lead time (days) | Days remaining | Flag | Owner | Backup | Submission system | Status | Confirmation | Source | Upcoming sort key
Formulas:
Days remaining = IF(OR([Internal deadline]="",[Status]="Submitted",[Status]="Confirmed",[Status]="Missed"),"",[Internal deadline]-TODAY())
Flag = IF(OR([Status]="Submitted",[Status]="Confirmed",[Status]="Missed"),"",IF(AND([Funder deadline]<>"",TODAY()>[Funder deadline]),"Past funder deadline",IF(AND([Internal deadline]<>"",TODAY()>[Internal deadline]),"Overdue",IF(AND([Days remaining]<>"",[Lead time (days)]<>"",[Days remaining]<=[Lead time (days)]),"Due soon",""))))

## Reporting Schedule
Reporting Schedule
Latest due dates the default federal rule allows (2 CFR 200.328(c) and (d) and 200.329(c)(1), eCFR, current as of September 2026). Your award document sets the actual dates.
Type the award's date in the Award date column and the tab uses it in place of the calculation. Delete any interim row your award does not require.
| Award or opportunity | [5 empty] | Calculated from your entries in column C
| Period of performance start | [5 empty] | months in each performance reporting period
| Period of performance end | [5 empty] | calendar days after each performance reporting period
| Performance report frequency | [5 empty] | months in each financial reporting period
| Financial report frequency | [5 empty] | calendar days after each financial reporting period
| Recipient or subrecipient | [5 empty] | calendar days after the period of performance for final reports
Copy each Due date used into the Deadline Log with Paste Special, Values, so the log keeps the date and not a formula.
Performance reports
# | Report | Period start | Period end | Default latest due date | Award date (type to override) | Due date used | Rule
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Financial reports
# | Report | Period start | Period end | Default latest due date | Award date (type to override) | Due date used | Rule
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Final reports
# | Report | Period start | Period end | Default latest due date | Award date (type to override) | Due date used | Rule
Final performance report
Final financial report
Formulas:
Period end = IF([Period start]="","",MIN(EDATE(C5,A13*G5)-1,C6))

## Upcoming
Upcoming
Open rows flagged Due soon, Overdue or Past funder deadline, in internal-deadline order. Filled by formulas from the Deadline Log; nothing to type here.
Flagged rows
A row with no internal deadline sorts by its funder deadline. The file sends nothing by itself: copy the filled rows into the weekly email to each owner and backup.
# | Internal deadline | Flag | Days remaining | Deliverable ID | Award or opportunity | Deliverable type | Funder deadline | Deadline time and zone | Owner | Backup | Status | Sort key (helper) | Log row (helper)

## Settings
Settings
The dropdown lists for the other tabs. Add your own deliverable types and submission systems in the white cells of columns A and C.
Keep the gray Status, Reporting frequency and Recipient type entries exactly as they are, because the formulas on the other tabs read them.
Deliverable type | Status (do not rename) | Submission system | Reporting frequency (do not rename) | Recipient type (do not rename)
Letter of intent | Not started | Grants.gov | Quarterly | Recipient
Pre-application | Drafting | eRA Commons | Semiannual | Subrecipient
Application | In review | Research.gov | Annual
Progress report | Submitted | eBRAP
Financial report | Confirmed | Sage
Final report | Missed | SAM.gov
Subaward report |  | Email
Registration renewal |  | Portal
Extension request