## Read Me
Grant Tracking Workbook
An Excel file meant to be opened in Google Sheets. One row per grant, one row per dated deliverable, formula flags for what is due, and a summary.
Read this first
Illustrative figures, not data from a real organization. Two sample grants, SAMPLE-01 and SAMPLE-02, show the formulas working; delete their rows on both the Grants and Deadlines tabs before you enter your own.
The workbook carries only the amounts requested and awarded. Spending stays off every tab: actual costs by budget line need a ledger with one row per transaction.
Some formulas use MINIFS, which older versions of Excel do not have. If a cell shows #NAME?, open the file in a current version of Excel or in Google Sheets.
How the workbook works
Grants | One row per grant: funder, type, stage, owner, amounts and award period. Next funder due and Open deliverables pull from the Deadlines tab by Grant ID.
Deadlines | One row per application, report or other dated deliverable, joined to its grant by Grant ID. A grant with an application, two interim reports and a final report takes one row on Grants and four here. Funder, Days to funder due and Flag are formulas.
Summary | Counts grants by stage, totals dollars requested and awarded, counts open, overdue and due-soon deliverables, and shows the next funder due date. Every figure comes from the Grants and Deadlines tabs.
Change Log | One row per change to a stage, a funder due date or an award amount, typed by hand: date, changed by, Grant ID, field, old value, new value and reason.
Lists | The allowed values for Type, Stage, Deliverable and Status, and the warning window in days (cell B2) that the Flag formula reads.
Color key
Typed input | White cells are typed inputs: grants, dates, owners, amounts and notes.
Formula | Light gray cells are formulas. Never type in them; they recalculate from the typed cells.
Who changes what
Tab | Owner
Grants
Deadlines
Summary
Change Log
Lists
Program staff update their own Deadlines rows.
One person owns the Grants tab and the Lists tab.
Nobody types in a shaded cell.
Walk each new staff member through these rules before giving edit access.
Keeping history
Mark a deliverable Cancelled instead of deleting its row. The row and its history stay, and the Days and Flag formulas ignore it.
Add a Change Log row whenever a stage, a funder due date or an award amount changes, with the reason, so an extension or a revised award is still explained later.
Save named versions at milestones, such as the day each report goes out. A spreadsheet can carry up to 15 named versions.
Due dates and flags
Days to funder due is the funder due date minus today's date, so it changes each day. It is blank once Status is Submitted or Cancelled; when a deliverable goes out, set Status to Submitted and type the date in Submitted on.
Flag shows Overdue once the funder due date passes with nothing submitted, Due soon when the date is within the warning window (14 days in Lists cell B2; change it once and every flag follows), and is otherwise blank.
The Flag column shows Overdue and Due soon to whoever opens the file and sends nothing. Google Sheets notification settings fire when the file changes or a form is submitted, not when a date arrives, so a date-based email needs Apps Script or a separate tool.
Copy funder due dates into a shared calendar as well, so the dates reach people who never open the sheet.
After opening in Google Sheets
Step 1 | Confirm that the formula columns show results and that the restricted columns (Type, Stage, Deliverable, Status) offer their lists.
Step 2 | Delete the two sample grants, SAMPLE-01 and SAMPLE-02: their rows on the Grants tab and on the Deadlines tab. Delete whole rows, so the formula cells below move up with them.
Step 3 | Enter each active grant once on the Grants tab and every dated deliverable on the Deadlines tab, with an owner on each row.
Step 4 | Set the warning window on the Lists tab.
Step 5 | Protect the shaded formula columns, the Summary and the Lists tab against accidental overwrites. Protection is not a security measure: treat anything in the file as readable by everyone it is shared with.
Step 6 | Name a version once the data is in.
Formula ranges
The formula columns are filled down to row 200 on Grants and row 500 on Deadlines; for more rows, copy the last formula row down. The Summary and the lookups read rows 2 to 1,000 of both tabs.
The formulas look for the Status values Submitted and Cancelled by name, and the Summary lists the six stages by name. Keep those spellings on the Lists tab, or change the formulas and the Summary to match.

## Summary
Summary
Illustrative figures, not data from a real organization. Every figure on this tab comes from the Grants and Deadlines tabs.
Grants by stage | Grants
Prospect
Drafting
Submitted
Awarded
Declined
Closed
Dollars requested |  | Sum of Amount requested on the Grants tab
Dollars awarded |  | Sum of Amount awarded on the Grants tab
Open deliverables |  | Deadlines rows with a Grant ID whose Status is not Submitted or Cancelled
Overdue |  | Deadlines rows whose Flag reads Overdue
Due soon |  | Deadlines rows whose Flag reads Due soon (warning window on the Lists tab)
Next funder due date |  | Earliest funder due date among open deliverables

## Grants
Grant ID | Funder | Grant or program | Type | Stage | Owner | Amount requested | Amount awarded | Decision date | Award start | Award end | Folder link | Next funder due | Open deliverables | Notes
SAMPLE-01 | Example Family Foundation (composite) | Example Youth Program | Foundation | Awarded | Development director | 30000 | 25000 | 2026-06-15 | 2026-07-01 | 2027-06-30 |  |  |  | Sample row. Delete once your own grants are in.
SAMPLE-02 | Example State Agency (composite) | Example Workforce Program | State or local | Prospect | Development director | 60000 | [7 empty] | Sample row. Delete once your own grants are in.

## Deadlines
Grant ID | Funder | Deliverable | Owner | Internal due | Funder due | Status | Submitted on | Days to funder due | Flag | Draft link | Notes
SAMPLE-01 |  | Application | Development director | 2026-02-20 | 2026-03-02 | Submitted | 2026-02-27 |  |  |  | Sample row. Delete once your own grants are in.
SAMPLE-01 |  | Interim report | Program manager | 2026-10-16 | 2026-10-30 | Submitted | 2026-10-28 |  |  |  | Sample row. Delete once your own grants are in.
SAMPLE-01 |  | Interim report | Program manager | 2027-01-15 | 2027-01-29 | In progress |  |  |  |  | Sample row. Delete once your own grants are in.
SAMPLE-01 |  | Final report | Program manager | 2027-07-16 | 2027-07-30 | Not started |  |  |  |  | Sample row. Delete once your own grants are in.
SAMPLE-02 |  | LOI | Development director | 2027-02-12 | 2027-02-26 | Not started |  |  |  |  | Sample row. Delete once your own grants are in.
Formulas:
Days to funder due = IF(OR([Grant ID]="",[Funder due]="",[Status]="Submitted",[Status]="Cancelled"),"",[Funder due]-TODAY())

## Change Log
Date | Changed by | Grant ID | Field | Old value | New value | Reason

## Lists
Lists
Warning window (days) | 14
Flag shows Due soon when the funder due date is this many days away or fewer.
Type | Stage | Deliverable | Status
Foundation | Prospect | LOI | Not started
Federal | Drafting | Application | In progress
State or local | Submitted | Interim report | Submitted
Corporate | Awarded | Final report | Cancelled
Other | Declined | Financial report
| Closed | Other